## Assembly Schedule
2014-01-15 16:34
Rugged Wear Work Boot Assembly Schedule
Assembly Line Balancing
Data |  |  |  |  | # stations | 1 | 1 | 1 | 1 | 1
| Priority rule | 5 |  |  |  | Priority rule
| Cycle time | 10 |  |  |  | 1 | 2 | 3 | 4 | 5
Lookup Criterion | Task Name | Task Time (Minutes) | Immediate Predecessors |  | Row number | Longest operation time | Most following tasks | Ranked Positional Weight | Shortest operation time | Least following tasks
0.1249 | A | 10 |  |  | 1 | 10 | 8 | 80 | 0.1 | 0.125
0.16647 | B | 6 | A |  | 2 | 6 | 6 | 60 | 0.16667 | 0.16667
0.16637 | C | 3 | A |  | 3 | 3 | 6 | 60 | 0.33333 | 0.16667
0.1996 | D | 8 | B,C |  | 4 | 8 | 5 | 50 | 0.125 | 0.2
0.33283 | E | 3 | D |  | 5 | 3 | 3 | 30 | 0.33333 | 0.33333
0.33273 | F | 4 | D |  | 6 | 4 | 3 | 30 | 0.25 | 0.33333
0.4993 | G | 3 | E,F |  | 7 | 3 | 2 | 20 | 0.33333 | 0.5
0.9992 | H | 9 | G |  | 8 | 9 | 1 | 10 | 0.11111 | 1
Station Assignments
Station |  | 1 | 2 | 2 | 3 | 4 | 4 | 4 | 5 | Sum | Minimum
Activities |  | A | B | C | D | E | F | G | H
Idle Time(orig. cycle time) |  | 0 |  | 1 | 2 |  |  | 0 | 1 | 4 | 0
Idle Time (improved cyc. time) |  | 0 |  | 1 | 2 |  |  | 0 | 1 | 4 | 0
Results Summary
Cycle time |  | C: 10
Time needed per cycle (S task times) |  | C: 46
Min (theoretical) # of stations |  | C: 5
Actual number of stations |  | C: 5
Improved cycle time = Maximum station cycle time |  | C: 10
Time allocated per cycle |  | C: 50
Idle time per cycle |  | C: 4
Efficiency |  | C: 92%
Balance delay | bar: C
Iterations (left to right)
Task Code (-1= Completed, 0 = Ready, N>0 = number of unmet precedences)
| Task |  | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 | Iteration 7 | Iteration 8
| A |  | 0 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1
| B |  | 1 | 0 | -1 | -1 | -1 | -1 | -1 | -1 | -1
| C |  | 1 | 0 | 0 | -1 | -1 | -1 | -1 | -1 | -1
| D |  | 2 | 2 | 1 | 0 | -1 | -1 | -1 | -1 | -1
| E |  | 1 | 1 | 1 | 1 | 0 | -1 | -1 | -1 | -1
| F |  | 1 | 1 | 1 | 1 | 0 | 0 | -1 | -1 | -1
| G |  | 2 | 2 | 2 | 2 | 2 | 1 | 0 | -1 | -1
| H | [8 empty] | 0 | -1 | bar: B to H
Selecting the next task
Time available |  |  | 10 | 0 | 4 | 1 | 2 | 7 | 3 | 0
Step 1a: Number of ready tasks that fit |  |  | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0
Step 1b: Adjust time if new station is needed |  |  | 10 | 10 | 4 | 10 | 10 | 7 | 3 | 10
Step 1c: Station |  |  | 1 | 2 | 2 | 3 | 4 | 4 | 4 | 5
Step 2a: Activity code |  |  | 0.1249 | 0.16647 | 0.16637 | 0.1996 | 0.33283 | 0.33273 | 0.4993 | 0.9992
Step 2b: Activity name |  |  | A | B | C | D | E | F | G | H
Step 2c: Activity time |  |  | 10 | 6 | 3 | 8 | 3 | 4 | 3 | 9
Time remaining |  |  | 0 | 4 | 1 | 2 | 7 | 3 | 0 | 1
Name check | Check that one name does not appear in another - e.g., A and AA or Task 1 and Task 10
|  | A | B | C | D | E | F | G | H
| A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| B | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| C | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| D | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| E | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| F | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| G | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| H | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computations of following tasks and ranked positional weight
The following table contains a 1 if row follows column
|  |  |  | Task name | Follows
|  | 0 | A | A | B,C | D | D | E,F | G
| A | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| B | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
| C | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
| D | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0
| E | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0
| F | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
| G | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
| H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | A | B | C | D | E | F | G | H
| A | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| B | 0 | 1 | 0 | 2 | 1 | 1 | 0 | 0
| C | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 0
| D | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 0
| E | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1
| F | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1
| G | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2
| H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | A | B | C | D | E | F | G | H
| A | 1 | 4 | 4 | 12 | 8 | 8 | 4 | 0
| B | 0 | 1 | 0 | 4 | 6 | 6 | 8 | 2
| C | 0 | 0 | 1 | 4 | 6 | 6 | 8 | 2
| D | 0 | 0 | 0 | 1 | 4 | 4 | 12 | 8
| E | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 6
| F | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 6
| G | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4
| H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | A | B | C | D | E | F | G | H | Num followers
| A | 1 | 8 | 8 | 56 | 112 | 112 | 280 | 224 | 8 | 80
| B | 0 | 1 | 0 | 8 | 28 | 28 | 112 | 140 | 6 | 60
| C | 0 | 0 | 1 | 8 | 28 | 28 | 112 | 140 | 6 | 60
| D | 0 | 0 | 0 | 1 | 8 | 8 | 56 | 112 | 5 | 50
| E | 0 | 0 | 0 | 0 | 1 | 0 | 8 | 28 | 3 | 30
| F | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 28 | 3 | 30
| G | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 2 | 20
| H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 10
|  | 10 | 6 | 3 | 8 | 3 | 4 | 3 | 9
Note on A10: Assembly Line Balancing: Submodel = 0; Problem size @ 8 by 2
Summary Table
Enter the cycle time below. You may need to compute it based on demand. Be certain the time unit (minutes, second, hrs) matches the task time unit. Enter the data for each task. Predecesors should be separated by commas. Enter a number between 1 and